## Sheet1
jana M Bug Report
Version No: |  |  |  | Verified By:
Tested By:Jisa John |  |  |  | Date:04/04/2022
Home Page
Bug ID | Expected Result | Bug Description | Steps to reproduce | Screenshot | Severity | Priority | Status
DEF_janm_01 | Biography should be Display | Jan M. Eckermann, MD, FAANS view bio button not working | 1.Open URL 2.Click View Bio button |  | Low |  | New
DEF_janm_02 | Our servic Content section should Correctly Alligned | our service SPINE content section points are not correctly alligned | 1.Open URL 2.Go to the our service section 3.check Spine content section |  | high |  | New
DEF_janm_03 | Contact Us section should correctly alligned | Contact us section not Correctly alligned | 1.Open URL 2.Go to the our service section 3.check Contact us section |  | low |  | New
DEF_janm_04 | All social media networks should working(Linkedin watsup,instagram) | all social media networks are not working | 1.Open URL 2.Go to the our service section 3.check footer social media section |  | low |  | New
DEF_janm_05 | Menu section links should working | Menu section links should not working | 1.Open URL 2.Go to the Menu bar |  | High |  | New
DEF_janm_06 | View all link section spelling should correct | View all link spelling mistake | 1.Open URL 2.Go to the View all services link secton |  | low |  | New
DEF_janm_07 | View all Veiw all services link should redirect | Veiw all services link not redirect | 1.Open URL 2.Go to the View all services link secton |  | High |  | New
DEF_janm_08 | Location Map zoom in/out should working | Location Map zoom in/out should not working | 1.Open URL 2.Go to the Location map section |  | Low |  | New
DEF_janm_09 | Instagram heading section should display | Instagram heading section not contain anything(Nothing contain in that portion) | 1.Open URL 2.Go to the Instagram heading section |  | Low |  | New
DEF_janm_10 | Mobile number should be redirect to the calling portion | Mobile number should not be redirect to the calling portion | 1.Open URL 2.Go to the Mobile Number Link part |  | Low |  | New
DEF_janm_11 | Content section of BRAIN and PAIN contain diffrent points | Content section of BRAIN and PAIN contain same points | 1.Open URL 2.Go to the Our Services section 3.Look BRAIN and PAIN section |  | Low |  | New